## Milestone 5
Step | Status | Description / Notes
1. Users table | Complete | Includes Role, PasswordHash, and IsActive.
2. Initial users | Complete | Admin and User accounts created.
3. BCrypt package | Complete | Using BCrypt.Net.
4. Password hashing | Complete | Passwords hashed during registration.
5. User model | Complete | Entity Framework model created.
6. Database login | Complete | Uses AppDbContext instead of raw SQL.
7. Verify password | Complete | Uses BCrypt.Verify().
8. Read role | Complete | Reads user.Role.
9. Generate JWT | Complete | JWT generation implemented.
10. Role claim | Complete | Uses ClaimTypes.Role.
11. JWT authentication | Complete | Working correctly.
12. Login response | Minor Improvement | Currently returns only token; add username and role.
13. Authorization | Improved | Uses record-level authorization (CustomerAccess).
14. Multiple roles | Future Enhancement | Not required yet.
15. Endpoint protection | Partial | Ownership enforced; DELETE should be Admin-only.
16. Authorization tests | Not Complete | Add 401/403 and ownership scenarios.

## Milestone 6
Priority | Task | Status | Notes
⭐⭐⭐⭐⭐ | Authorization test coverage | To Do | Admin/Owner/401/403 scenarios.
⭐⭐⭐⭐ | Repository layer | Optional | Separate data access from controllers.
⭐⭐⭐ | Refresh tokens | Optional | Enterprise enhancement.
⭐⭐⭐⭐ | Global exception middleware | To Do | Centralized error handling.
⭐⭐⭐ | API versioning | Optional | /api/v1, /api/v2.
⭐⭐⭐⭐⭐ | ILogger logging | To Do | Structured logging.
⭐⭐⭐ | Rate limiting | Optional | Protect login endpoint.
⭐⭐⭐ | Security headers / HTTPS | Optional | Production hardening.

## Interview Readiness
Item | Status
CRUD API | Complete
SQL Server integration | Complete
Stored procedures | Complete
Input validation | Complete
JWT authentication | Complete
Database-backed users | Complete
BCrypt password hashing | Complete
Role claims | Complete
Record-level authorization | Complete
Soft deletes | Complete
Swagger security | Complete
Audit / Sync logging | Complete
Authorization-focused tests | Recommended Next
README + architecture diagram | Recommended
Interview presentation/demo script | Recommended