## Implementation Status
DemoERP – Current Implementation Status
Summary
Progress | 75%
Completed | 11
Improved | 1
Minor Improvements | 1
Partially Complete | 1
Remaining | 1
Future Enhancements | 1
Overview | 11 Complete · 1 Improved · 1 Minor Improvement · 1 Partial · 1 Remaining
Step # | Status | Feature | Description / Comments | Priority | Notes
1 | Complete | Users Table | Includes Role, PasswordHash, and IsActive fields. | High
2 | Complete | Initial User Accounts | Default Admin and User accounts have been created. | High
3 | Complete | BCrypt Integration | BCrypt.Net package installed and configured for secure password hashing. | High
4 | Complete | Password Hashing | User passwords are securely hashed during registration. | High
5 | Complete | User Entity Model | Entity Framework User model implemented successfully. | High
6 | Complete | Database Authentication | Authentication uses AppDbContext instead of raw SQL queries. | High
7 | Complete | Password Verification | Passwords are validated using BCrypt.Verify(). | High
8 | Complete | Role Retrieval | User role is retrieved from the database (user.Role). | High
9 | Complete | JWT Token Generation | GenerateToken(role) implemented successfully. | High
10 | Complete | JWT Role Claims | JWT includes ClaimTypes.Role for authorization. | High
11 | Complete | JWT Authentication | JWT generation and validation are fully operational. | High
12 | Minor Improvement | Login Response | Currently returns only the JWT token. Recommend returning token, username, and role. | Medium
13 | Improved | Authorization Model | Resource-based (record-level) authorization implemented, providing finer-grained access control than role-only authorization. | High
14 | Future Enhancement | Multiple Roles | Multi-role support can be added if future requirements change. | Low
15 | Partially Complete | Endpoint Protection | Ownership-based authorization is implemented. Consider restricting DELETE operations to Admin users only. | Medium
16 | Not Complete | Authorization Test Coverage | Add comprehensive authorization tests covering Admin, Owner, Anonymous, Invalid JWT, 401 Unauthorized, and 403 Forbidden scenarios. | High